## Sheet1
Activity Date W/C | Event Date | Event | Marketing Mix Element | Target Group | Specific Marketing Activity | Who | Status | Notes
2015-03-30 | 2015-05-20 | The Man Whose Memories Fell Out | Release of show. | Online | Release of image on social media | Alice | Complete
2015-03-30 | 2015-05-20 | The Man Whose Memories Fell Out | Social Media | Online | Create online event | Alice | Complete
2015-03-30 | 2015-05-20 | The Man Whose Memories Fell Out | Social Media | Online | Sharing of information online | Whole cast | Complete
2015-04-20 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | Visitors to LPAC | Distrubute leaflets in LPAC | Alice | Complete
2015-04-20 | 2015-05-20 | The Man Whose Memories Fell Out | Distribtion | General Public | Distribute leaflets around Lincoln | Alice | Complete
2015-04-20 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | Visitors to LPAC | Display posters in LPAC | Alice | Complete
2015-04-20 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | General Public | Display posters around Lincoln | Alice | Complete
2015-04-27 | 2015-05-20 | The Man Whose Memories Fell Out | Press | General Public | Radio Siren FM | Alice Arrange | Complete | Moved to week commencing 4/05
2015-04-27 | 2015-05-20 | The Man Whose Memories Fell Out | Press | General Public | Send out press release | Alice | Complete | Get contacts
2015-05-04 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | General Public | Flyering in city centre | Alice plus… | Complete | Contact Lincoln Big
2015-05-04 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | General Public | Flyering in city centre | Alice plus… | Complete | Contact Lincoln Big
2015-04-04 | 2015-05-20 | The Man Whose Memories Fell Out | Social Media | Online | Launch competition | Alice | Complete | Moved to week commencing 11/05
2015-05-04 | 2015-05-20 | The Man Whose Memories Fell Out | Email | Students | Email students | Alice | Complete
2015-05-18 | 2015-05-20 | The Man Whose Memories Fell Out | Press | General Public | BBC Lincolnshire interview? | Alice Arrange | Complete | Contact BBC Lincoln
2015-05-18 | 2015-05-20 | The Man Whose Memories Fell Out | Distribution | General Public | Flyering in city centre | Alice plus… | Complete